# Quality Improvement Template

| Practice name: | Add your primary healthcare service name here | Date: | Add date of commencement here |
| --- | --- | --- | --- |
| QI team: | List the team members involved |  |  |
| Problem: | Describe why this work is strategically important. What problem is the team addressing? What does our data indicate about it, and what are the causes? |  |  |
| Problem Statement: | Document your succinct problem statement here |  |  |

This document guides practice staff through the Model for Improvement (the Thinking Part) and the Plan-Do-Study-Act (PDSA) cycle (the Doing Part), a framework for planning, testing, and reviewing changes.

For guidance and support on conducting quality improvement in your primary healthcare services, please contact your local Primary Health Network (PHN).

# Model for Improvement

Step 1: Thinking Part - Three Fundamental Questions Complete the Model for Improvement (MFI) as a whole team.

| AIM | - What are we trying to accomplish? |  |  |
| --- | --- | --- | --- |
| By answering this question, you will develop your GOAL for improvement. It important to establish a S.M.A.R.T (Specific, Measurable, Achievable, Relevant, Time bound) and people-crafted aim that clearly states what you are trying to achieve. |  |  |  |
| Ensure that 95% of patients with chronic conditions (e.g. diabetes, hypertension, COPD) have correctly coded conditions in their medical records within the next six months, with a focus on MyMedicare enrolment. |  |  |  |
| MEASURE(S) | - How will we know that a change is an improvement? |  |  |
| By answering this question, you will develop the MEASURE(S) you will use to track your overarching goal. Record and track your baseline measurement to allow for later comparison. Tip: Use a Run Chart to plot trends. |  |  |  |
| Percentage of patient records with correctly coded chronic conditions (e.g. diabetes, hypertension, COPD) , and the proportion of these patients enrolled in MyMedicare. |  |  |  | Percentage of patient records with correctly coded chronic conditions (e.g. diabetes, hypertension, COPD) , and the proportion of these patients enrolled in MyMedicare. |  |  |
| Baseline: | • Active patients = 4000 • Coded Diabetes = 200 • Indicated diabetes and not diagnosed = 150 • MyMedicare enrolled = 50 | Baseline date: | 15/9/2026 |
| CHANGE IDEAS | - What changes can we make that will result in improvement? |  |  |
| By answering this question, you will develop IDEAS for change. Tip: Engage the whole team in formulating change ideas using tools such as brainstorming, driver diagrams or process mapping. Include any predictions and measure their effect quickly. |  |  |  |
| Idea 1 | Identify a cohort of patients with diabetes, and review for coding accuracy. |  |  |
| Idea 2 | Train clinical staff on best practices for chronic condition coding. |  |  |
| Idea 3 | Include MyMedicare enrolment as part of the coding review process. |  |  |
| Idea 4 |  |  |  |
| Idea 5 | Add other rows if needed. |  |  |
| Next steps: | Each idea may involve multiple short and small PDSA cycles. |  |  |

PDSA (Plan-Do-Study-Act)

Step 2: Doing Part - Plan-Do-Study-Act Once you have completed the Model for Improvement (MFI), use the template below to document and track your PDSA cycles (i.e. small rapid tests of change).

| Idea | Plan |  | Do | Study | Act |
| --- | --- | --- | --- | --- | --- |
| # | Plan the test | Prediction | Do the test on small scale | Analyse the results | Make a plan for next step |
|  | How will we run this test? Who will do it and when? What will we measure? | Prediction or hypothesis on what will happen. | Was the plan completed? Yes or No. Collect data. Consider what worked well and why? Document any unexpected observations, events or problems. | Analyse results, compare them to predictions, and reflect on what you learned. . | Based on your learnings from the test, what will you do next (e.g., adopt, adapt or abandon)? How does this inform the plan for your next PDSA? |
| Change idea 1.1 | Identify a cohort of patients with diabetes, and revie for coding accuracy Prediction: inconsistent coding and free-text of conditions | Completed on 1/6/26 | Principal GP to review 150 patients with indicated and not diagnosed patients. The majority 80 patients have pre-diabetes and 45 were overdue for a HBA1C test. 5 were inactive patients. 10 were on metformin relating to polycystic ovary syndrome, 20 were incorrectly coded and the remaining 35 patient were provided to other GPs for investigation. | Schedule a clinician meeting to create a uniform coding for diabetes and update clinical coding policy. Invite PHN to present to your team on the importance of clinical coding. | Identify a cohort of patients with diabetes, and revie for coding accuracy Prediction: inconsistent coding and free-text of conditions. |
|  | Keep adding rows and cycles as needed. |  |  |  |  |
| Change idea 1.2 Introduce a new change idea if required | Schedule a clinician meeting to create a uniform coding for diabetes and update clinical coding policy. | Clinical meeting held 2/3/26 | 5 out of 7 GPs attend this meeting. 3 of the GPs were not aware of comment and provisional diagnosis fields and therefore have been freetexting diagnosis. Reason for visit was also defaulting to add to patient history due to BP preference settings. This was fixed for all GPs. | PMs preference settings to be fixed for all GPs to not enforce reason for visit to be added automatically to patient history. | Schedule a clinician meeting to create a uniform coding for diabetes and update clinical coding policy. |
| 1.2.1 | Introduce a new change idea if required. Keep adding rows and cycles as needed. |  |  |  |  |
| Summary of Results |  |  |  |  |  |